## Sheet1
Week | Focus | Key Deliverables | Success Criteria
Week 1 (This week) | Foundation & Core Accuracy | • v3 JSON schema + improved extraction • Real pricing integration (spreadsheet + DB) • Smart Make / Buy / Buy+Manufacture logic • Preliminary Pricing Spreadsheet | • Accurate JSON on 80%+ of test drawings • Live priced quotes using real costs on 5–10 drawings • Preliminary spreadsheet with full workings |  | Suggested compressed timeline
Week 2 | Scale, Polish & Validation | • Process full batch of drawings • RAG / knowledge base for common parts & suppliers • Nesting & utilisation improvements • Risk scoring + review dashboard • Finalise Pricing Spreadsheet | • 90%+ drawings priced automatically • Complete, well-documented Pricing Spreadsheet • RAG system live for supplier lookups & standards |  | Week 1 (now)
Week 3 | Production Readiness & Handover | • Database integration (your 4 tables) • Quote output templates (PDF/Excel) • Edge case handling framework • User guide + training session • Final testing & refinement | • System can price “all” current drawings with clear flags • MD/FS can use it confidently • Ready for live rollout |  | Freeze schema + pricing audit model.
Integrate DB/spreadsheet lookups.
Week | Phase | Key Focus Areas | Main Deliverables | Success Criteria | Validate on 10 drawings.
1 | Foundation & Real Pricing | v3 JSON accuracy + real cost integration | • Cleaner v3 JSON schema • Smart Make/Buy/Buy+Manufacture classification • PricingService connected to your spreadsheet + DB • Preliminary Pricing Spreadsheet with full workings | Live priced quotes on 10+ drawings using your real rates | Week 2
2 | Scale & Validation | Batch processing + RAG | • Full batch processing pipeline • RAG system for common parts/suppliers • Nesting & utilisation engine • Risk scoring dashboard | 90%+ of standard drawings priced automatically | Batch runner + variance report (manual vs auto).
3 | Production Readiness | Output formats + DB integration | • Your 4 database tables fully integrated • Professional quote templates (PDF/Excel) • User guide + training • Initial testing round | System usable by sales/estimating team | Prioritise top variance causes and patch logic quickly.
4–5 | Refinements & Edge Cases | Handling non-standard drawings | • Improved handling of client concept files (PPTs, images, non-vector PDFs) like the Gillette Mobile Cage • Better assumption generation for incomplete data • Enhanced geometry / OCR for poor drawings • Expanded RAG for bespoke items | Accurate pricing on mixed / concept-level drawings with transparent assumptions | Deliver first internal estimator trial.
6–7 | Bespoke & Resilience | Advanced edge cases + unknowns | • Logic for highly custom / non-standard items • Automated flagging + partial estimates for unknown drawings • Continuous learning loop (feedback from manual overrides) • Performance optimisation & final testing | System handles almost all incoming drawings reliably. Only occasional manual tweaks needed for brand-new bespoke designs | Week 3
DB integration hardening, output templates, user workflow.
Add RAG only where it clearly improves repeated component pricing.
Week 4
Edge-case module (concept docs/non-vector PDFs) + fallback assumptions.
Release candidate to sales/estimating.